## PAS
MOM Date | 2022-07-07
Attendees
Rameshwar Kakade <rkakade@chemito.net>; Bhavesh Jivani <bjivani@chemito.net>; Omkar Jadhav <ojadhav@chemito.net>; Nagaraj Suresh <nsuresh@chemito.net>; nitin.bahri <nitin.bahri@heinrichlimited.com>; Shangloo, Akhil (SMO RI LCE EPE-COC PE) <akhil.shangloo@siemens.com>
Sl.No | Description | Responsible | Action | Target Date
1 | TFT Protocol document | Ms.Chemito | Chemito team will share updated document | 2022-07-11
2 | Scrolling Message jerk issue | Ms.Chemito | Chemito team working on jerk issue | 2022-07-15
3 | video with message on TFT not playing properly | Ms.Chemito | Chemito team working | 2022-07-15
4 | LED Protocol document | Ms.HEINRICH | Heinrich team need to test | 2022-07-11
5 | PAS PIDS Integrated FAT demonstration | Ms.HEINRICH | Heinrich team need to install software and testing need to start | 2022-07-11